## ชีต1
PartyTube MVP - Task Breakdown & WBS
Total Tasks |  | Total Est. Hours
19 |  | 82
Task ID | Category | Task Name | Description | Complexity | Priority | Est Hours | Status | AI Prompt Context | Test Target / Spec
DB-01 | Database | MySQL & Prisma Schema Setup | Define Room, QueueItem, and GuestSession models in schema.prisma, create initial migration and seed script | Low | High | 3 | Todo | Prompt AI to write Prisma schema with relations and indexes | Prisma CLI migration test
BE-01 | Backend | NestJS Project Scaffolding & PrismaModule | Initialize NestJS with TypeScript, configure ConfigModule, PrismaModule, global validation pipe, and CORS | Low | High | 3 | Todo | Prompt AI to scaffold NestJS and wire up PrismaService | Healthcheck endpoint test
BE-02 | Backend | Rooms Service & Controller | Implement POST /api/rooms and GET /api/rooms/:code with 6-char code generator and hostToken hashing | Medium | High | 4 | Todo | Prompt AI to implement RoomsService with collision-safe code generation | RoomsController unit test
BE-03 | Backend | Queue Service Business Logic | Implement FIFO queue methods (addTrack, getNextTrack, reorderQueue, removeTrack, updateStatus) with Prisma transactions | High | High | 6 | Todo | Prompt AI to write QueueService with concurrency protection | QueueService unit tests (TEST-01)
BE-04 | Backend | YouTube API Proxy & LRU Cache | Build YouTube search service using youtube-sr (Quota-free InnerTube scraper) + YouTube URL parser fallback, with in-memory caching to support unlimited searches. | Medium | High | 4 | Todo | Prompt AI to implement YouTubeService with youtube-sr library and regex URL parser (supports youtu.be, shorts, and watch URLs). | YouTubeService unit tests (TEST-02)
BE-05 | Backend | Socket.io Real-time Gateway | Implement PartyGateway with @WebSocketGateway, room rooms (room:code), join, leave, and queue event dispatchers | High | High | 6 | Todo | Prompt AI to implement NestJS WebSocket gateway with Socket.io adapter | PartyGateway E2E test (TEST-04)
FE-01 | Frontend | Next.js App Router Setup & Tailwind UI | Initialize Next.js with Tailwind CSS, Lucide icons, Dark party theme, and shared TypeScript DTO types | Low | High | 4 | Todo | Prompt AI to configure Next.js App Router layout with Tailwind theme | Lint and build test
FE-02 | Frontend | WebSocket Client Hook (usePartySocket) | Create custom React hook for Socket.io connection, room subscription, reconnection handling, and Zustand state | High | High | 5 | Todo | Prompt AI to implement usePartySocket hook with state sync | Socket hook unit test
FE-03 | Frontend | Landing & Host Room Creation UI | Build Landing Page with 'Create Party' button, Room Code display, and react-qr-code generator for TV screen | Low | High | 3 | Todo | Prompt AI to build responsive landing page and QR code modal | Component render test
FE-04 | Frontend | Host View - YouTube Player Engine | Build Big-Screen TV player using react-youtube, auto-next on video end (YT.PlayerState.ENDED), and host controls | High | High | 6 | Todo | Prompt AI to build HostPlayer component with playback error handling | Player state trigger test
FE-05 | Frontend | Guest View - Mobile Join & Search Flow | Build mobile search UI with YouTube URL auto-detection (instant Add on paste) and debounced keyword search showing live YouTube results. | Medium | High | 5 | Todo | Prompt AI to build SearchBar with regex detecting YouTube URLs on paste and calling live search endpoint for text keywords. | Search component test
FE-06 | Frontend | Guest View - Live Queue & Toast Feedback | Build mobile tabs for Live Queue, showing Now Playing, Up Next list with 'Added by' badges, and toast notifications | Medium | High | 4 | Todo | Prompt AI to build QueueTab component with Sonner toasts | Queue component test
TEST-01 | Testing | QueueService Unit Test Suite | Write Jest unit tests for QueueService covering FIFO order, auto-next pop, duplicate prevention, and reordering | Medium | High | 4 | Todo | Prompt AI to generate comprehensive Jest unit tests for QueueService | 100% Queue logic coverage
TEST-02 | Testing | YouTubeService Unit Test Suite | Write Jest unit tests for YouTube search proxy, caching behavior, and YouTube API error/quota fallback mocks | Low | High | 3 | Todo | Prompt AI to generate Jest tests mocking googleapis and cacheManager | Mocked API & cache test
TEST-03 | Testing | Prisma & MySQL Integration Tests | Write integration tests using Testcontainers or test MySQL database verifying foreign key cascades and transactions | Medium | High | 4 | Todo | Prompt AI to create Jest integration test suite with Prisma | Database CRUD & transaction test
TEST-04 | Testing | WebSocket Gateway E2E Tests | Write E2E tests connecting multiple socket.io-client instances simulating Host and Guests joining and syncing queue | High | High | 5 | Todo | Prompt AI to write supertest / socket.io-client test script | Multi-socket event sync test
TEST-05 | Testing | Playwright Frontend E2E Flow | Write Playwright test covering Host room creation -> Guest join via URL -> Guest search & add song -> Host auto-play | High | High | 6 | Todo | Prompt AI to write Playwright end-to-end test script | Full browser E2E test
DEV-01 | DevOps | Docker Compose & Local Dev Setup | Create docker-compose.yml with MySQL 8.0, Adminer, and hot-reloading for NestJS and Next.js | Low | High | 3 | Todo | Prompt AI to generate docker-compose.yml and .env.example files | Docker compose up verification
DEV-02 | DevOps | Production Deployment & CI/CD | Setup GitHub Actions CI for lint/test, deploy NestJS + MySQL to Railway/Render, and Next.js to Vercel | Medium | High | 4 | Todo | Prompt AI to write GitHub Actions workflow and deployment configs | Automated CI build test